## Tabelle1
Phase	Task ID	Task	Duration	Dependencies	Milestone
1. Planning	1.1	Define Requirements & Features	5 days	—	✔
	1.2	AR Market & Competitor Analysis	3 days	—
	1.3	Technology Stack Selection	2 days	1.1
2. Design	2.1	UX/UI Design for AR HUD	5 days	1.1, 1.3
	2.2	Game Mechanics & Logic Draft	4 days	1.1	✔
3. Development	3.1	AR Environment Setup	5 days	2.1
	3.2	Tetris Game Logic Programming	8 days	2.2
	3.3	AR Integration (game + hardware)	6 days	3.1, 3.2	✔
	3.4	Multiplayer/Scoreboard Logic	5 days	3.2
4. Testing & QA	4.1	Unit Testing	3 days	3.2, 3.4
	4.2	AR Field Testing	4 days	3.3	✔
	4.3	Bug Fixes & Optimization	4 days	4.1, 4.2
5. Release	5.1	Prepare Launch & Marketing	3 days	4.3
	5.2	Deployment on App Stores	2 days	5.1	✔